## Week1
# | Sub-Task | Description | Deliverables | Tools / Languages | Review Criteria
1 | Understand Dataset Structure | Analyze all CSVs from the Olist dataset: list each table’s columns, data types, sample values, and identify primary/foreign keys. Map how tables relate to each other. 梳理所有表格字段和关系 | olist_schema_summary.md olist_column_samples.xlsx | Python (Pandas), Markdown, Excel | All tables documented; each column described with type/sample; FK/PK relations clearly listed and mapped.
2 | Draft Cleaning and Transformation Plan | Document data cleaning logic for each table: how to handle missing values, inconsistent types, and outliers. Describe column renaming and feature formatting rules. 为数据清洗与字段标准化制定计划 | data_cleaning_plan.md | Python (Pandas), Markdown | Each table included; every column’s cleaning strategy explained; all assumptions and decisions logged.
3 | Design ER Diagram and Schema | Design an ER diagram representing table relationships. Write schema specs including normalization (3NF) and reasoning behind structure. 绘制ER图并数据库规范化设计 | ERD.drawio or ERD.png relational_schema.md | Draw.io, PostgreSQL (DDL), Markdown | ERD complete and accurate; table-to-table links valid; normalization correctly applied or explained.
4 | Write SQL for Table Creation | Develop SQL DDL script to create tables in PostgreSQL: include types, constraints, PKs, and FKs. Create indexes for join/filter efficiency. 建表脚本 定义字段、主外键、约束及索引 | create_tables.sql | PostgreSQL | Script runs without errors; table structure matches schema design; constraints and indexes correctly defined.
5 | Build Python ETL Pipeline | Code a Python ETL script to read, clean, and load CSVs into PostgreSQL. Integrate error handling and logging. 用Python实现完整ETL流程 包含数据导入、转换与异常处理 | etl_pipeline.py requirements.txt | Python, Pandas, SQLAlchemy or psycopg2 | All tables loaded successfully; logs complete; data cleaned as per plan.
6 | Validate Loaded Data | After running ETL, use SQL or Python to check row counts, FK integrity, and consistency with original data. Include basic profiling (min/max/nulls). 验证数据导入 检查数据完整性和基本统计指标 | etl_validation_report.md data_summary_by_table.csv | SQL, Python | Loaded data verified; FKs intact; summaries confirm successful transformation and loading.
7 | Create Analytical Views | Create SQL views that join common tables such as customers, orders, and products. These will support downstream analytics. 构建便于后续分析的视图 | init_views.sql | PostgreSQL | Views run without error; content verified to support EDA and demand forecasting tasks.

## Week2
# | Sub-Task | Description | Deliverables | Review Criteria
1 | Time Series Aggregation | Aggregate key metrics (daily/weekly/monthly orders, revenue, customer count) across time and entities (state, category, seller). 按时间维度对销售指标进行汇总，分析销售节奏变化 | eda_timeseries_summary.ipynb timeseries_plots.png | All plots readable; trends clearly annotated; different time aggregations (day/week/month) correctly compared.
2 | Sales Distribution Comparison | Compare order counts and revenues by state, product category, and seller. Use heatmaps, histograms, and bar charts. 从地域、品类、卖家角度分析销量分布差异 | sales_distribution_analysis.ipynb category_state_heatmap.png, top_sellers_bar.png | Insights backed by data; visualizations labeled and interpreted; top segments identified.
3 | Product Performance Overview | Identify best-selling and least-selling products using descriptive stats (mean, variance, order frequency). 识别高销量与低销量商品，为后续选品策略提供依据。 | product_performance_stats.csv product_ranking.md | Product list ranked; metrics clearly defined; threshold rules explained.
4 | Holiday Mapping | Map Brazilian holidays (especially Christmas, Mother’s Day, Black Friday, etc.) into the dataset. Mark these days in order timeline. 将巴西主要节假日与订单数据对齐，方便进行节日影响分析 | holiday_mapping_table.csv holiday_annotation_function.py | All major holidays mapped; code can dynamically flag holidays in timeline.
5 | Holiday vs. Regular Day Sales Analysis | Compare order volume, AOV (Average Order Value), and delay across holiday vs. regular days. Visualize difference and run t-tests. 节假日与非节假日销售表现差异分析，量化节日效应和可视化 | holiday_sales_comparison.ipynb holiday_vs_normal_day_chart.png | Difference clearly visualized; statistical results included; product/region-level comparison included.
6 | Holiday-Sensitive Product Analysis | Identify which products/categories exhibit significant demand change during holidays. Highlight top holiday-sensitive SKUs.找出受节日影响最显著的商品和类目，为库存调整提供参考。 | holiday_sensitive_products.csv sensitivity_analysis_report.md | Threshold logic stated; results justified; business implications summarized.
7 | Summary Report | Create a markdown report summarizing all Week 2 findings, including key graphs and preliminary business implications. 探索性分析报告 | eda_week2_summary.md key_visuals.zip | Logical flow; includes key insights; ready to be referenced in white paper and later slides.

## Week3
# | Sub-task | Description | Deliverables | Evaluation Criteria
1 | Customer Behavior Feature Engineering | Extract user-level features for fulfillment, including number of orders, total and average spending, product category diversity, freight ratio, and time gaps between purchases. 用户行为特征提取（订单数、消费金额、最近活跃时间、购买多样性、是否有退货行为） | customer_logistics_features.csv 包含每位用户的行为汇总特征 | 支持后续 RFM 与生命周期分析
2 | RFM Scoring and Logistics-Aware Segmentation | Apply Recency-Frequency-Monetary scoring and cluster customers, incorporating freight cost and delivery region tags. 基于 RFM 和物流偏好进行分群 | rfm_segmented_customers.csv（包含RFM分数、标签、地理物流标签） | 需要合理分群，带有指向性（如多地订单）
3 | Geolocation Mapping of Segments | Visualize customer segments across geographic regions (states, cities), identify distribution trends and fulfillment bottlenecks. 地理视角下可视化分群用户分布，识别区域物流风险（但是从数据上来看这部分可能作用不大，因为绝大部分订单都顺利完成了） | customer_cluster_geolocation.csv，州/城市分布图、Choropleth Map | 区域聚集
4 | Customer Lifecycle + Churn Classification | Classify users into New, Active, At-risk, and Churned stages using recency thresholds; tag fulfillment-priority users. 使用购买时间划分生命周期阶段，结合优先级打标签 | customer_lifecycle.csv（生命周期阶段、churn标签） | 支持后续结合下单时间等情况考虑仓配调度
5 | Purchase Funnel Dropout Analysis | Analyze behavioral funnel stages (e.g., ordered, delivered) and identify where users drop off. 分析从下单到收货的行为路径与流失阶段 | orders_with_funnel_tag.csv，路径图、dropout sankey | 路径流程明晰，流失点定位有效
6 | Unified Customer Persona Table | Merge all user-level outputs to form a full persona table, enriched with ordering time patterns and product category preference. 统一行为+分群+时间偏好+地理+商品偏好的客户画像 | final_customer_segments.csv，Persona 分布可视化图表 | 到这一步，用户类型标签已完整，支持下一步的推荐/预测建模
7 | Product Preference Segmentation | Analyze each customer’s dominant categories, diversity, loyalty to certain types, and category entropy. Segment customers as specialists/generalists/premium buyers. 基于step6的结果，基于商品偏好的独立聚类分析（step6中只是汇总了用户下单多的商品品类，没有用于分群），除了关注用户主要购买品类的忠诚度（是否反复下单相同类型商品），单价喜好（对于特定品类，会选择什么价位的） | / | 用户对商品品类的购买宽度及与消费水平的差异

## Week4
Task # | Sub-task | Description | Deliverables | Tools / Techniques | Evaluation Criteria
1 | Sales Curve Construction | Construct time-series sales curves per product to observe lifecycle trends. 构建每个商品的销售时间序列曲线，观察生命周期走势（如引入、成长期） | Time-series plots, annotated lifecycle stages | Python (Pandas, Matplotlib), Rolling averages | Curves show clear trends, lifecycle inflection points can be identified
2 | Product Lifecycle Classification | Label products based on volume, growth rate, and saturation patterns into 4 stages: Introduction, Growth, Maturity, Decline. 根据销量水平、增长趋势、饱和度等指标划分商品生命周期阶段 | Lifecycle labels CSV, summary statistics by stage | Rule-based classification or supervised learning | Classification aligns with observed trends; balanced distribution
3 | Inventory Efficiency Analysis | Measure stock levels, turnover rates, and holding costs for different product stages. 分析不同生命周期阶段商品的物流和库存水平、周转率与仓储成本 | Inventory turnover table, cost heatmaps | SQL / Python (Calc metrics), Business rules | Efficiency gaps are clear, cost drivers are interpretable
4 | Overstock / Stockout Risk Analysis | Identify SKUs at risk of overstock or stockout using threshold rules or statistical models. 通过规则或模型识别过剩/缺货风险商品 | Risk flag table, anomaly detection report | Thresholding + IQR/z-score or isolation forest | Precision/recall of risk flags validated via business logic
5 | Inventory Policy Suggestion | Suggest differentiated stock policies based on lifecycle stage and volatility. 针对不同生命周期与波动率商品制定差异化库存管理策略 | Policy matrix, rule recommendations (markdown / PPT) | Rule-based matrix, business-case simulation | Recommendations are interpretable and minimize cost vs. service level
6 | Warehouse Resource Allocation Simulation | Run simulations to test how changing storage space, replenishment frequency affects fulfillment rate. 模拟不同仓储配置、补货频率对发货成功率的影响 | Simulation notebook, KPI output graphs | Python (SimPy / custom logic), Optimization heuristics | Scenario results are valid and recommendations actionable
7 | Summary Report & Strategic Insight | Compile lifecycle analytics, risks, warehouse optimization into a report. 整理生命周期分析与仓储策略为一份分析报告 | Lifecycle summary report, PowerPoint briefing slides | PDF + PPT export or HTML dashboard | Insightful, compact, and directly supports inventory decision-making

## Week5
Task # | Sub-task | Description | Deliverables | Tools / Techniques | Evaluation Criteria
1 | Seller Product Geography Time Analysis | Comprehensive analysis of seller performance across product categories, geographic regions, and time periods to identify patterns and opportunities.全面分析卖家在产品类别、地理区域和时间维度上的表现，识别模式和机会 | seller_product_geography_time_analysis.csv, geographic_performance_heatmap.png, temporal_trend_analysis.csv | Python (Pandas, NumPy), Geographic analysis, Temporal analysis, Product category analysis | Analysis reveals clear geographic and temporal patterns; performance metrics are comprehensive; insights support strategic decisions
2 | Seller Lifecycle Product Strategy Analysis | Analyze seller lifecycle stages and develop product strategy recommendations based on growth patterns, market position, and competitive dynamics.分析卖家生命周期阶段，基于增长模式、市场地位和竞争动态制定产品策略建议 | seller_lifecycle_analysis.csv, product_strategy_recommendations.csv, lifecycle_stage_classification.csv | Python (Pandas, NumPy), Lifecycle analysis, Strategy development, Market positioning | Lifecycle stages are clearly defined; strategy recommendations are actionable; market positioning is accurate
3 | Seller Fulfillment Complexity Analysis | Assess seller fulfillment complexity based on order volume, product diversity, geographic distribution, and operational efficiency metrics.基于订单量、产品多样性、地理分布和运营效率指标评估卖家履约复杂性 | seller_fulfillment_complexity.csv, complexity_scoring_matrix.csv, operational_efficiency_metrics.csv | Python (Pandas, NumPy), Complexity scoring, Efficiency analysis, Operational metrics | Complexity scores are reasonable; efficiency metrics are comprehensive; operational insights are actionable
4 | Seller Warehouse Demand Analysis | Analyze seller-specific warehouse demand patterns including storage requirements, peak periods, and seasonal variations for capacity planning.分析卖家特定的仓库需求模式，包括存储需求、高峰期和季节性变化，用于容量规划 | seller_warehouse_demand.csv, demand_pattern_analysis.csv, capacity_planning_insights.csv | Python (Pandas, NumPy), Demand forecasting, Pattern analysis, Capacity planning | Demand patterns are clearly identified; capacity planning insights are practical; seasonal variations are captured
5 | Regional Fulfillment Load Projection | Project regional fulfillment load requirements based on seller distribution, order patterns, and geographic demand concentration for strategic warehouse placement.基于卖家分布、订单模式和地理需求集中度预测区域履约负荷需求，用于战略仓库布局 | regional_fulfillment_load.csv, load_projection_analysis.csv, strategic_warehouse_placement.csv | Python (Pandas, NumPy), Load projection, Geographic analysis, Strategic planning | Load projections are realistic; geographic analysis is comprehensive; strategic recommendations are actionable

## Week6
Task # | Sub-task | Description | Deliverables | Tools / Techniques | Evaluation Criteria
1 | Time Series Feature Engineering | Extract and engineer comprehensive time series features from historical data including temporal, seasonal, trend, and lag features for forecasting models. 从历史数据中提取和构建全面的时间序列特征，包括时间、季节性、趋势和滞后特征，用于预测模型 | week6_time_series_features_matrix.csv, feature_importance_analysis.csv, feature_correlation_matrix.csv | Python (Pandas, NumPy), Feature engineering, Statistical analysis, Correlation analysis | Feature matrix is comprehensive; features show predictive power; correlation analysis reveals meaningful relationships
2.1 | Statistical Forecasting | Implement traditional statistical forecasting methods including ARIMA, Exponential Smoothing, and Seasonal Decomposition for baseline predictions. 实现传统统计预测方法，包括ARIMA、指数平滑和季节性分解，用于基准预测 | statistical_forecasts.csv, model_performance_metrics.csv, forecast_accuracy_reports.csv | Python (Statsmodels), ARIMA modeling, Exponential smoothing, Seasonal decomposition | Statistical models provide stable baseline; forecast accuracy is reasonable; model diagnostics are satisfactory
2.2 | Machine Learning Forecasting | Implement advanced ML forecasting methods including ensemble models, gradient boosting, and neural networks for improved prediction accuracy. 机器学习预测方法，包括集成模型、梯度提升和神经网络，以提高预测准确性 | ml_forecasts.csv, model_performance_comparison.csv, feature_importance_ranking.csv | Python (Scikit-learn), Ensemble methods, Gradient boosting, Neural networks | ML models outperform statistical baselines; feature importance is interpretable; model performance is consistent
2.3 | Deep Learning Forecasting | Implement deep learning forecasting methods including LSTM, GRU, and Transformer models for complex temporal pattern recognition. 深度学习预测方法，包括LSTM、GRU和Transformer模型，用于复杂时间模式识别 | dl_forecasts.csv, deep_learning_performance_metrics.csv, model_architecture_reports.csv | Python (TensorFlow/Keras), LSTM networks, GRU networks, Transformer models | Deep learning models capture complex patterns; performance metrics are competitive; model architectures are appropriate
2.4 | Model Ensemble | Combine predictions from multiple models using ensemble methods including voting, stacking, and weighted averaging for optimal forecast accuracy. 使用集成方法组合多个模型的预测，包括投票、堆叠和加权平均，以获得最佳预测准确性 | ensemble_forecasts.csv, ensemble_performance_metrics.csv, model_weights_analysis.csv | Python (Scikit-learn), Ensemble methods, Model stacking, Weighted averaging | Ensemble forecasts are more accurate than individual models; ensemble weights are optimized; performance is robust
2.5 | Order Count Forecasting | Specifically forecast order_count using ensemble approach with Linear Regression and Voting Regressor for capacity planning.专门使用集成方法预测 order_count，包括线性回归和投票回归器，用于容量规划 | order_count_forecasts.csv, order_count_performance_metrics.csv, capacity_planning_insights.csv | Python (Scikit-learn), Linear Regression, Voting Regressor, Ensemble forecasting | Order count forecasts are accurate; forecasts support capacity planning; performance metrics are reasonable
3.1 | Basic Capacity Calculation | Calculate basic warehouse capacity requirements including storage space, labor hours, and equipment needs based on demand forecasts. 基于需求预测计算基本仓库容量需求，包括存储空间、工时和设备需求 | basic_capacity_calculations.csv, capacity_requirements_summary.csv, resource_allocation_plans.csv | Python (Pandas, NumPy), Capacity modeling, Resource allocation algorithms, Demand-driven calculations | Capacity calculations are realistic; resource requirements are reasonable; calculations support operational planning
3.2 | Advanced Capacity Optimization | Implement advanced capacity optimization algorithms including multi-objective optimization, constraint handling, and cost-benefit analysis for optimal resource allocation. 容量优化算法，包括多目标优化、约束处理和成本效益分析，用于最优资源分配 | advanced_capacity_optimization.csv, optimization_results_summary.csv, cost_benefit_analysis.csv | Python (SciPy), Multi-objective optimization, Constraint programming, Cost-benefit analysis | Optimization results are feasible; cost-benefit ratios are favorable; constraints are properly handled
3.3 | Capacity Prediction Integration | Integrate all capacity prediction results and create comprehensive capacity planning framework with scenario analysis and risk assessment. 整合所有容量预测结果，综合容量规划框架，包括情景分析和风险评估 | capacity_prediction_integration.csv, scenario_analysis_results.csv, risk_assessment_summary.csv | Python (Pandas, NumPy), Integration algorithms, Scenario analysis, Risk assessment | Integration provides comprehensive view; scenario analysis covers multiple cases; risk assessment is thorough

## Week7
Task # | Sub-task | Description | Deliverables | Tools / Techniques | Evaluation Criteria
1.1 | Cost-Benefit Analysis Engine (Main) | Orchestrate data loading, comprehensive cost-benefit analysis, visualization generation, and output saving for warehouse strategy decisions.第一个子任务的主文件。协调数据加载、全面成本效益分析 | cost_benefit_analysis.csv, financial_metrics_summary.csv, sensitivity_analysis_results.csv | Python (Pandas, NumPy), Dynamic module loading, Error handling, Data validation | Main engine successfully orchestrates all components; handles missing data gracefully; generates comprehensive outputs
1.2 | Cost-Benefit Calculations | Encapsulate core calculation logic for cost-benefit analysis including fixed costs, variable costs, benefits calculation, and financial metrics computation 成本效益分析的核心计算函数，包括固定成本、可变成本、收益计算和财务指标计算 | Internal calculation results, Financial metrics (ROI, NPV, IRR), Cost structure analysis | Python (NumPy), Financial modeling, Cost allocation algorithms, Revenue prediction models | Calculations produce reasonable financial metrics; cost structure is logical; revenue projections are realistic
1.3 | Cost-Benefit Analysis | Advanced analysis methods for cost-benefit analysis including sensitivity analysis, Monte Carlo simulation, risk-adjusted metrics, and optimization recommendations.成本效益分析的函数，包括敏感性分析、蒙特卡洛模拟、风险调整指标 | sensitivity_analysis_results.csv, monte_carlo_simulation_results.csv, optimization_recommendations.csv | Python (SciPy), Monte Carlo simulation, Sensitivity analysis, Statistical modeling | Sensitivity analysis identifies key drivers; Monte Carlo results are stable; optimization recommendations are actionable
2.1 | Risk Assessment and Mitigation (Main) | Orchestrate data loading, comprehensive risk assessment, visualization, and output saving for risk-aware decision making.第二个子任务的主文件。全面风险评估、可视化和输出保存 | risk_assessment_results.csv, scenario_analysis_results.csv, monte_carlo_simulation_results.csv | Python (Pandas, NumPy), Dynamic module loading, Risk scoring models, Scenario analysis | Main engine successfully identifies and quantifies risks; generates comprehensive risk assessment; handles multiple risk categories
2.2 | Risk Assessment Calculations | Core risk calculation logic including demand risk, operational risk, market risk, and financial risk assessment with probability and impact-based scoring.核心风险计算函数，包括需求风险、运营风险、市场风险和财务风险评估。还有一个基于概率和影响的评分 | Internal risk calculations, Risk scoring results, Risk factor analysis | Python (NumPy), Probability models, Impact assessment, Risk scoring algorithms | Risk scores are within reasonable ranges; risk factors are properly weighted; calculations are mathematically sound
2.3 | Risk Analysis and Mitigation | Advanced risk analysis methods including scenario analysis, Monte Carlo simulation, risk monitoring metrics, and recommended actions generation. 风险分析函数，包括情景分析、蒙特卡洛模拟、风险监控指标和推荐行动生成 | scenario_analysis_results.csv, risk_monitoring_metrics.csv, recommended_actions.csv | Python (SciPy), Scenario modeling, Monte Carlo simulation, Risk mitigation strategies | Scenario analysis covers optimistic/base/pessimistic cases; Monte Carlo results are stable; mitigation strategies are specific
3.1 | Precision Recommendation Generator (Main) | Orchestrate data loading, recommendation generation, visualization, and output saving for actionable warehouse strategy decisions.第三个子任务的主文件。推荐生成、可视化和输出保存 支持仓库策略决策 | precision_recommendations.csv, implementation_plans.csv, monitoring_dashboards.csv | Python (Pandas, NumPy), Dynamic module loading, Multi-dimensional integration, Recommendation scoring | Main engine successfully integrates multiple data sources; generates diverse recommendation types; creates actionable implementation plans
3.2 | Recommendation Calculations | Core recommendation calculation logic including multi-dimensional analysis integration, comprehensive scoring, and ROI estimates for different recommendation types. 推荐计算函数，包括多维度分析集成、综合评分和不同推荐类型的ROI估算 | Internal recommendation calculations, Comprehensive scores, ROI estimates | Python (NumPy), Multi-dimensional analysis, Scoring algorithms, ROI calculation models | Calculations produce reasonable priority scores; ROI estimates are realistic; recommendation types are diverse
3.3 | Recommendation Analysis | Advanced recommendation analysis methods including implementation plan generation, expected benefits prediction, monitoring metrics design, and feasibility assessment. 推荐分析函数，包括实施计划生成，，效益预测 和可行性评估 | implementation_plans.csv, expected_benefits.csv, feasibility_reports.csv | Python (Pandas), Implementation planning, Benefit prediction models, Feasibility assessment | Implementation plans are detailed and realistic; benefit predictions are quantifiable; feasibility assessments are comprehensive
4.1 | Recommendation Validation and Optimization (Main) | Orchestrate comprehensive validation including historical backtesting, Monte Carlo simulation, expert review, A/B testing design, and optimization recommendations.第四个子任务的主文件。验证，包括历史回测、专家评审、A/B test | validation_results.csv, optimization_recommendations.csv, ab_test_designs.csv | Python (Pandas, NumPy), Dynamic module loading, Validation orchestration, Error handling | Main engine successfully coordinates all validation methods; handles data structure variations; generates comprehensive validation results
4.2 | Validation Calculations | Core validation calculation logic including historical backtest validation, Monte Carlo simulation, validation metrics calculation, and performance benchmarks.验证计算函数，包括历史回测验证、蒙特卡洛模拟、验证指标计算 | historical_backtest_results.csv, monte_carlo_validation_results.csv, performance_benchmarks.csv | Python (NumPy, SciPy), Historical backtesting, Monte Carlo simulation, Statistical validation | Backtest accuracy >85%; Monte Carlo results are stable; validation metrics are comprehensive
4.3 | Validation Analysis | Advanced validation analysis methods including expert review system, A/B test design, optimization recommendations generation, and validation dashboard metrics. 验证分析方法的函数封装，包括专家评审系统、A/B测试的细节 | expert_review_results.csv, ab_test_designs.csv, validation_dashboard_metrics.csv | Python (Pandas), Expert review systems, A/B test design, Optimization algorithms | Expert review scores >80%; A/B test designs are statistically sound; optimization recommendations are actionable

## Week8
Task # | Sub-task | Description | Deliverables | Tools / Techniques | Evaluation Criteria
1 | Full White Paper Writing | Write a professional, structured white paper including all major components. 包含完整分析流程和商业价值体现的项目白皮书（准备用latex格式） | Final White Paper (PDF, ~15–25 pages) | MS Word / LaTeX / Markdown → PDF | Completeness, structure, language clarity
2 | Section-by-Section Refinement | Refine all key sections: Executive Summary, Data Overview, Methods, Analysis, Forecasting, Dashboard, and Recommendations. 分析模块逐个检查打磨，确保逻辑顺畅、语言严谨 | Updated versions of each white paper section | Grammarly / Notion / Peer Review | Internal consistency, technical depth, fluency
3 | Visual Consistency Check | Standardize plots, charts, and dashboards visuals (colors, fonts, legends) across the document. | Final plots/images; updated PPTs or inserts | matplotlib, seaborn, Canva, PowerPoint | Visual coherence and professionalism
4 | Final Business Recommendations | Consolidate all findings into 3–5 actionable recommendations for e-commerce decision makers. 提炼核心建议并形成建议清单，选品、定价、库存、物流 | Business summary (in report and separate slide) | Business writing, summary tables | Clarity, practicality, relevance to stakeholders
5 | Final Submission to Platform | Submit white paper, presentation, code, and supporting files as per project requirement. 整理后上船 GitHub | Submission ZIP / folder / GitHub repo | Google Drive, Moodle, GitHub | Completeness, correct format
6 | Poster or Showcase Slide Preparation | / | Slide deck or poster (PDF / PPT / PNG) | PowerPoint / Canva / Illustrator | Informative, appealing, concise